## Gantt Chart
GANTT CHART - NBA basketball game prediction | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | NBA basketball game prediction |  |  |  |  | COMPANY NAME | [6 empty] | [Company's name]
PROJECT MANAGER |  | Ivan Li |  |  |  |  | DATE | [6 empty] | 2018-03-12
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Information Collection
1.1 | Project Manage | Ivan Li | 2020-11-06 | 2020-11-22 | 16 | 100% | bar: WEEK 1 F to WEEK 2 T
1.1.1 | Searching for Research paper | Ivan Li | 2020-11-06 | 2020-11-11 | 5 | 100% | bar: WEEK 2 W
1.1.2 | Reading research paper | Ivan Li | 2020-11-12 | 2020-11-19 | 7 | 100% | bar: WEEK 2 R to WEEK 3 R
1.1.3 | Evaluate research paper | Ivan Li | 2020-11-20 | 2020-11-22 | 2 | 100% | bar: WEEK 3 M to WEEK 3 R
2 | Literature review Planning
2.1 | Identify themes, debates and gaps | Ivan Li | 2020-11-23 | 2020-11-26 | 3 | 100% | bar: WEEK 4 M to WEEK 4 R
2.2 | Outline the structure | Ivan Li | 2020-11-27 | 2020-11-30 | 3 | 100% | bar: WEEK 4 F to WEEK 5 F
2.3 | Write literature review | Ivan Li | 2020-12-01 | 2020-12-20 | 19 | 12%
3 | Data Collection
3.1 | Resolve ethical issue | Ivan Li |  |  | 0 | 0%
3.2 | ensure data validation | Ivan Li |  |  | 0 | 0%
3.2.1 | Analysis data | Ivan Li |  |  | 0 | 0%
3.2.2 | Sorting data | Ivan Li |  |  | 0 | 0%
3.3 | Investigate data | Ivan Li |  |  | 0 | 0%
3.3.1 | Reanalysis data and writing result | Ivan Li |  |  | 0 | 0%
4 | Product design
4.1 | Product development | Ivan Li |  |  | 0 | 0%
4.2 | Tableau interface design | Ivan Li |  |  | 0 | 0%
4.3 | End user expereience analysis | Ivan Li |  |  | 0 | 0%
4.4 | Modify and finalise | Ivan Li |  |  | 0 | 0%